## Plan with Time AR
اسم المشروع: حكايات تيتة وجدو
خطة تنفيذ لمدة 90 يومًا لمشروع يجمع بين التصوير البشري والرسم ثنائي الأبعاد والتحريك والمونتاج.
ملاحظات | النشاط | التاريخ | اليوم
المرحلة الأولى: التحضير والتصوير البشري (الأيام 1–30)
تثبيت مدة الفيديو، صيغة التسليم، والنسخة المطلوبة. | تحديد نطاق المشروع ومخرجاته النهائية |  | 1
تحديد فكرة الحكاية والرسالة الأساسية. | مراجعة فكرة حكايات تيتة وجدو |  | 2
تحديد مشاهد البيت ومشاهد الحكاية المرسومة. | مراجعة السيناريو وتقسيمه |  | 3
حصر الشخصيات البشرية والمرسومة واحتياجات كل شخصية. | تحديد الشخصيات وأدوارها |  | 4
ترقيم المشاهد وتحديد موقع كل مشهد ونوعه. | إعداد قائمة المشاهد |  | 5
مراجعة تسلسل اللقطات مع روان وتحديد التعديلات. | مراجعة الـ Storyboard |  | 6
توحيد شكل الشخصيات والألوان وطريقة الحركة. | تحديد أسلوب الرسم والتحريك |  | 7
تجميع مراجع للملابس والتعبيرات والأوضاع. | إعداد مراجع بصرية للشخصيات |  | 8
تحديد المشاهد والممثلين والمكان والأدوات. | تجهيز خطة التصوير البشري |  | 9
حصر الكاميرا أو الهاتف والإضاءة والصوت والحامل. | تجهيز قائمة الأدوات والمعدات |  | 10
توزيع المهام ومواعيد التسليم بين الأعضاء. | تحديد مسؤوليات أعضاء الفريق |  | 11
تحديد نظام تسمية للقطات والرسومات وملفات المشروع. | إنشاء مجلدات وتنظيم الملفات |  | 12
إضافة أرقام المشاهد واللقطات وملاحظات الأداء. | تجهيز نسخة تصوير من السيناريو |  | 13
حصر الحوار والموسيقى والمؤثرات والأصوات المطلوبة. | تحديد احتياجات الصوت |  | 14
حصر المهام التي يمكن دعمها بأدوات AI بعد مراجعة النتائج. | تحديد احتياجات الذكاء الاصطناعي |  | 15
تحديد أحجام اللقطات وزوايا الكاميرا وحركة الممثلين. | تجهيز قائمة اللقطات |  | 16
اختبار الخلفية والإضاءة وتقليل الضوضاء البصرية. | مراجعة جاهزية موقع التصوير |  | 17
تصوير لقطة تجريبية وفحص الصورة والصوت. | اختبار تصوير قصير |  | 18
تسجيل الملاحظات وتعديل الإضاءة أو زاوية الكاميرا. | مراجعة اختبار التصوير |  | 19
مراجعة السيناريو والـ Storyboard وجدول التصوير قبل التنفيذ. | اعتماد خطة ما قبل الإنتاج |  | 20
تنفيذ أول مجموعة من مشاهد تيتة وجدو. | بدء تصوير مشاهد البيت |  | 21
تسجيل الحوار مع ترك مساحة لإعادة اللقطات. | تصوير لقطات الحوار |  | 22
تسجيل لقطات قريبة وتفاصيل داعمة للمونتاج. | تصوير ردود الأفعال واللقطات الإضافية |  | 23
التأكد من وضوح الحوار وثبات الإضاءة. | مراجعة جودة الصوت والصورة |  | 24
استكمال اللقطات غير الواضحة أو غير المكتملة. | إعادة تصوير اللقطات الناقصة |  | 25
حفظ نسخة إضافية من كل المواد المصورة. | نسخ ملفات التصوير احتياطيًا |  | 26
تقسيم الملفات حسب المشهد واللقطة. | فرز اللقطات وتصنيفها |  | 27
تحديد اللقطات الصالحة للمونتاج الأولي. | اختيار أفضل اللقطات |  | 28
ترتيب اللقطات وفق تسلسل السيناريو. | إعداد تجميعة أولية للمشاهد البشرية |  | 29
حصر أي مشاهد أو تفاصيل ما زالت ناقصة. | مراجعة اكتمال التصوير البشري |  | 30
المرحلة الثانية: الرسم والتحريك والمونتاج الأولي (الأيام 31–60)
مراجعة الرسومات النهائية للشخصيات الأساسية. | استكمال تصميم الشخصيات |  | 31
تجهيز التعبيرات اللازمة للحوار والانفعالات. | رسم تعبيرات الوجه |  | 32
تجهيز الوضعيات المطلوبة لكل مشهد. | رسم أوضاع الشخصيات |  | 33
التأكد من ثبات الملامح والنسب بين الرسومات. | مراجعة تناسق الشخصيات |  | 34
فصل العناصر وتنظيم الطبقات حسب الحاجة. | تجهيز ملفات الرسم للتحريك |  | 35
إعداد الخلفيات المتوافقة مع الـ Storyboard. | تجهيز خلفيات المشاهد |  | 36
توضيح بداية الحركة ونهايتها وتوقيتها. | تحديد حركة كل لقطة مرسومة |  | 37
تحريك لقطة قصيرة لاختبار الأسلوب. | إعداد اختبار حركة للشخصيات |  | 38
تسجيل ملاحظات السرعة والتعبير وسلاسة الحركة. | مراجعة اختبار التحريك |  | 39
تنفيذ المشاهد ذات الأولوية حسب ترتيب الحكاية. | بدء تحريك المشاهد الأساسية |  | 40
تنفيذ الحركات المطلوبة للحوار وردود الأفعال. | تحريك حركات الوجه والجسم |  | 41
تجهيز الانتقالات البصرية اللازمة بين اللقطات. | تحريك الانتقالات داخل المشاهد |  | 42
ضبط تزامن الحركة مع الكلام عند الحاجة. | مراجعة توقيت التحريك مع الحوار |  | 43
إنهاء بقية اللقطات المرسومة وفق الخطة. | استكمال تحريك المشاهد |  | 44
فحص ثبات الخطوط والألوان وعدم وجود قفزات. | مراجعة جودة الرسوم المتحركة |  | 45
تجربة الأدوات في مهام مساندة فقط ومراجعة الناتج يدويًا. | تجهيز عناصر مساعدة باستخدام AI عند الحاجة |  | 46
تصحيح العيوب البصرية في العناصر المعتمدة. | تنظيف العناصر أو الخلفيات المساندة |  | 47
تجهيز عنوان حكايات تيتة وجدو وأسماء المشاركين. | إعداد التتر الافتتاحي |  | 48
تجهيز أسماء الفريق والاعتمادات بدقة. | إعداد تتر النهاية وشكر الفريق |  | 49
جمع الحوار والموسيقى والمؤثرات المرخصة أو المتاحة للاستخدام. | تجهيز ملفات الصوت الأولية |  | 50
تقليل الضوضاء مع الحفاظ على طبيعية الأصوات. | تنقية الحوار عند الحاجة |  | 51
تسمية النسخ وتحديد المشاهد المكتملة والناقصة. | تنظيم ملفات التحريك النهائية |  | 52
إخراج المشاهد بصيغ مناسبة للمونتاج. | تصدير مشاهد التحريك |  | 53
تجربة ترتيب المشاهد وتحديد نقاط الدمج. | مزامنة ملفات التحريك مع المشاهد البشرية |  | 54
ترتيب المشاهد البشرية والمرسومة حسب السيناريو. | بدء المونتاج التجميعي |  | 55
تحسين توقيت القطع والانتقال بين العالمين. | ضبط الإيقاع والانتقالات |  | 56
مراجعة التناسق البصري بين المشاهد المختلفة. | دمج التصوير البشري مع التحريك |  | 57
ضبط مستويات الصوت وتوقيت المؤثرات. | إضافة الحوار والموسيقى والمؤثرات |  | 58
عرض نسخة أولية للفريق وتسجيل الملاحظات. | مراجعة النسخة التجميعية الأولى |  | 59
تقسيم الملاحظات حسب المشهد والأولوية والمسؤول. | إعداد قائمة تعديلات واضحة |  | 60
المرحلة الثالثة: المراجعة والتعديلات والتسليم (الأيام 61–90)
تطبيق الملاحظات المعتمدة على الصورة والصوت. | تنفيذ تعديلات النسخة الأولى |  | 61
تحديد اللقطات الناقصة وإنتاجها أو استبدالها. | استكمال أي لقطات ناقصة |  | 62
إصلاح الحركات غير المتناسقة أو التوقيت غير المناسب. | تصحيح أخطاء التحريك |  | 63
مراجعة القطع وتتابع المشاهد واستمراريتها. | تصحيح أخطاء المونتاج |  | 64
التأكد من تناسق الأداء والملابس والإضاءة بين اللقطات. | مراجعة استمرارية التصوير البشري |  | 65
التأكد من اتساق الشخصيات والخلفيات. | مراجعة تناسق الرسم والألوان |  | 66
مراجعة التزامن النهائي عند وجود حوار مرسوم. | ضبط الحوار مع حركة الشخصيات |  | 67
التأكد من وضوح الحوار وعدم تغطية الموسيقى عليه. | مراجعة الموسيقى والمؤثرات |  | 68
تدقيق عنوان المشروع والأسماء الظاهرة. | مراجعة التتر الافتتاحي |  | 69
تدقيق أسماء الفريق والأدوار. | مراجعة تتر النهاية |  | 70
تصدير نسخة بعد التعديلات الرئيسية. | إعداد نسخة ثانية للمراجعة |  | 71
رصد أي خلل في الإيقاع أو الصوت أو الصورة. | مشاهدة النسخة كاملة دون توقف |  | 72
حصر الملاحظات المتبقية في قائمة واحدة. | تجميع الملاحظات النهائية |  | 73
إغلاق الملاحظات المؤكدة حسب الأولوية. | تنفيذ التصحيحات النهائية |  | 74
التأكد من ملاءمة العناصر المساعدة وعدم وجود عيوب واضحة. | مراجعة استخدام عناصر AI |  | 75
التحقق من صلاحية استخدام الموسيقى والصور والعناصر الخارجية. | مراجعة الحقوق والمصادر |  | 76
ضبط مستوى الحوار والموسيقى والمؤثرات. | توحيد مستويات الصوت |  | 77
تحسين التناسق بين اللقطات البشرية قدر الإمكان. | تصحيح الألوان والإضاءة |  | 78
اختيار إعدادات التصدير المناسبة لمتطلبات التسليم. | مراجعة دقة الصورة ومعدل الإطارات |  | 79
اختبار التصدير قبل إخراج النسخة النهائية. | تصدير نسخة تجريبية عالية الجودة |  | 80
التأكد من سلامة الصورة والصوت وعدم وجود إطارات سوداء. | فحص النسخة المصدرة |  | 81
التأكد من أن الحجم مناسب للتسليم أو المشاركة. | مراجعة حجم الملف |  | 82
تقليل الحجم مع الحفاظ على جودة مقبولة. | ضغط الملف عند الحاجة |  | 83
تصدير النسخة النهائية بالصيغة المطلوبة. | تجهيز النسخة النهائية |  | 84
حفظ الفيديو النهائي وملفات المشروع الأساسية. | إنشاء نسخة احتياطية نهائية |  | 85
ترتيب الفيديو والرسومات والصوت والملفات المرجعية. | تنظيم ملفات التسليم |  | 86
توثيق مسؤولية كل عضو والمخرجات التي أنجزها. | تجهيز ملخص مساهمات الفريق |  | 87
التأكد من موافقة الفريق على النسخة النهائية. | مراجعة أخيرة مع الفريق |  | 88
تسليم الفيديو والملفات المطلوبة والاحتفاظ بنسخة احتياطية. | تسليم المشروع |  | 89
تسجيل ما تم إنجازه والملاحظات المستفادة. | إغلاق المشروع وتوثيق النتائج |  | 90

## Plan with Time EN
Project Name: Hekayat Teta w Gedo (Grandma and Grandpa Stories)
A 90-day production plan combining live-action filming, 2D character design and animation, editing, sound, and final delivery.
Day | Date (2025) | Task(s) | Notes
Stage 1: Pre-production and Live-Action Filming (Days 1–30)
1 |  | Define project scope and deliverables | Confirm target duration, delivery format, and required version.
2 |  | Review the project concept | Clarify the story idea and its main message.
3 |  | Review and break down the script | Separate the live-action home scenes from animated story scenes.
4 |  | List characters and their roles | Identify live-action and animated characters and their needs.
5 |  | Create a scene list | Number scenes and identify location and scene type.
6 |  | Review the storyboard | Review shot sequence with Rowan and identify revisions.
7 |  | Define the animation style | Align character appearance, colors, and movement style.
8 |  | Collect visual references | Gather references for clothing, expressions, and poses.
9 |  | Prepare the live-action shoot plan | List scenes, performers, location, and equipment.
10 |  | Prepare an equipment checklist | Check camera/phone, lighting, audio, and tripod.
11 |  | Assign team responsibilities | Set task ownership and internal deadlines.
12 |  | Organize project folders | Set naming rules for footage, artwork, and project files.
13 |  | Prepare a shooting script | Add scene and shot numbers plus performance notes.
14 |  | List audio requirements | Identify dialogue, music, sound effects, and required voices.
15 |  | Identify suitable AI-assisted tasks | Select support tasks for AI tools and plan human review.
16 |  | Prepare a shot list | Define shot sizes, camera angles, and actor movement.
17 |  | Check the filming location | Test background, lighting, and visual distractions.
18 |  | Record a short camera test | Capture a test shot and check picture and sound.
19 |  | Review the camera test | Note changes needed to lighting or camera angle.
20 |  | Approve pre-production readiness | Confirm script, storyboard, and shoot schedule.
21 |  | Begin filming home scenes | Film the first group of Grandma and Grandpa scenes.
22 |  | Film dialogue shots | Record dialogue and allow time for retakes.
23 |  | Capture reactions and inserts | Record close-ups and supporting details for editing.
24 |  | Check picture and sound quality | Ensure dialogue is clear and lighting is consistent.
25 |  | Reshoot missing or unclear shots | Complete shots that are unclear or incomplete.
26 |  | Back up the footage | Keep a second copy of all recorded material.
27 |  | Sort and label footage | Organize clips by scene and shot.
28 |  | Select the best takes | Mark footage suitable for the rough cut.
29 |  | Create a rough assembly of live-action scenes | Arrange selected clips in script order.
30 |  | Check live-action coverage | List any missing scenes or details.
Stage 2: Character Art, Animation, and Rough Editing (Days 31–60)
31 |  | Complete character designs | Review final artwork for the main characters.
32 |  | Draw facial expressions | Prepare expressions needed for dialogue and emotion.
33 |  | Draw character poses | Prepare poses required by each scene.
34 |  | Check character consistency | Keep features and proportions consistent across drawings.
35 |  | Prepare artwork for animation | Separate and organize layers where needed.
36 |  | Prepare scene backgrounds | Create backgrounds matching the storyboard.
37 |  | Define motion for each animated shot | Specify movement start, end, and timing.
38 |  | Create an animation test | Animate a short shot to test the chosen style.
39 |  | Review the animation test | Note timing, expression, and smoothness changes.
40 |  | Animate key scenes | Prioritize and animate the main story scenes.
41 |  | Animate face and body movement | Create the required dialogue and reaction movements.
42 |  | Create scene transitions | Prepare visual transitions where needed.
43 |  | Check animation timing against dialogue | Adjust synchronization where applicable.
44 |  | Continue animating remaining scenes | Complete the remaining planned animated shots.
45 |  | Review animation quality | Check line consistency, colors, and movement continuity.
46 |  | Use AI tools for support where appropriate | Test AI only for suitable assisting tasks and review results manually.
47 |  | Clean up supporting assets | Correct visual issues in approved supporting elements.
48 |  | Create the opening title | Prepare the project title and opening credits.
49 |  | Create end credits and acknowledgements | Prepare accurate team names and credits.
50 |  | Prepare initial audio assets | Collect dialogue, music, and usable sound effects.
51 |  | Clean dialogue audio if needed | Reduce noise while keeping voices natural.
52 |  | Organize final animation files | Label versions and track completed and pending scenes.
53 |  | Export animated scenes | Export shots in formats suitable for editing.
54 |  | Sync animation with live-action footage | Test scene order and integration points.
55 |  | Start the rough cut | Arrange live-action and animated scenes according to the script.
56 |  | Refine pacing and transitions | Improve cuts and transitions between the two visual worlds.
57 |  | Combine live action and animation | Check visual consistency across scene types.
58 |  | Add dialogue, music, and sound effects | Balance audio levels and timing.
59 |  | Review the first assembled version | Watch a rough version and record team feedback.
60 |  | Create a revision list | Group notes by scene, priority, and owner.
Stage 3: Review, Revisions, and Final Delivery (Days 61–90)
61 |  | Apply first-round revisions | Implement approved picture and sound notes.
62 |  | Complete missing shots | Produce or replace any missing footage or animation.
63 |  | Fix animation errors | Correct awkward movement or timing.
64 |  | Fix editing errors | Check cuts, scene order, and continuity.
65 |  | Check live-action continuity | Review performance, clothing, and lighting consistency.
66 |  | Check artwork and color consistency | Ensure character and background visuals match.
67 |  | Review dialogue synchronization | Check final timing for animated dialogue.
68 |  | Review music and sound effects | Keep dialogue clear and audible.
69 |  | Review the opening title | Verify project title and displayed names.
70 |  | Review end credits | Verify team names and role credits.
71 |  | Export a second review version | Create a version incorporating major revisions.
72 |  | Watch the full version without interruption | Identify pacing, sound, or picture issues.
73 |  | Consolidate final notes | Collect remaining feedback in one list.
74 |  | Complete final corrections | Close confirmed notes by priority.
75 |  | Review AI-assisted assets | Check suitability and remove visible defects.
76 |  | Check asset rights and sources | Confirm external music, images, and assets can be used.
77 |  | Balance audio levels | Adjust dialogue, music, and effects.
78 |  | Correct color and lighting | Improve consistency across live-action shots.
79 |  | Confirm export settings | Choose suitable resolution and frame rate.
80 |  | Export a high-quality test | Test the export before final rendering.
81 |  | Inspect the exported file | Check audio, picture, and any black frames.
82 |  | Review file size | Ensure the file is practical for delivery and sharing.
83 |  | Compress if needed | Reduce size while preserving acceptable quality.
84 |  | Export the final version | Render the final video in the required format.
85 |  | Back up final materials | Save the final video and essential project files.
86 |  | Organize delivery folders | Arrange video, artwork, audio, and reference files.
87 |  | Prepare a team contribution summary | Document each member's role and deliverables.
88 |  | Conduct a final team review | Confirm team approval of the final version.
89 |  | Deliver the project | Submit the video and required files and retain a backup.
90 |  | Close the project and document outcomes | Record completed work and lessons learned.